## Checklist
| Feature | Implemented
1 | User onboarding and management
| Web3 connection & authentication | Done
| User profile | Done
| Integration with Twitter | Done
2 | Collections |  |  | Web testing: | https://mumbai.another-1.io/launchpad/
| Search & List collections | Done |  | Use case: | Use Cases - Dandelion Labs x Another-1 - ISO Launchpad - Google Docs
| Collection profiles | Done
| NFT profiles | Done
3 | Minting Portal
| Sale periods definition & sales templates | Done
| Private sale for whitelisted addresses | Done
| Public sale | Done
5 | Redemption
| Redemption request (phase 1) | Done
| NFC integration (phase 2) | Done
| Authentication Function (phase 3) | Done
| Admin panel function to set NFC ID | Done
| Forging | Done
6 | Socials
| Follow creators | Done
| Like NFTs | Done
| Collection watchlist | Done
7 | Socials report
| Report users | Pending
| Report collection/NFT issues | Pending
8 | Whitelist
| Add to whitelist | Done
9 | Creators onboarding
| Become a creator page | Pending
| Process documentation | Pending
| Checklist for requirements | Done
10 | Documentation
| User manual documentation | Pending
11 | Corporate
| Landing page | Done
| FAQ | Done
12 | Redeployments
| Redeployments NTR1 | Done
| Redeployments Nayom1 | Done
13 | Admin Panel - Phygital |  | Main Focus
| - Set redemption window | Done
| - Set redemption attributes | Done
| - NFT-NFC | Done
- Analytics
14 | Admin Panel - Collection management
| - Set mint limit | Done
| - Set sales period | Done
| - Slot reservation (mint hold) | Done
| - Collection profile edit | Done
| - Whitelist | Done
| - Analytics | Done
15 | Admin Panel - User management
| - Role & permission management | Done
| - Blacklist | Done
16 | Security
| Integration with Fractal | Done
| Alert system (Launchpad down) | Done

## Report Testing
| Feature | Test case writing | Number of test case | Testing
1 | User onboarding and management | Done | 14
Web3 connection & authentication
User profile
Integration with Twitter
2 | Collections | Done | 6
Search & List collections
Collection profiles
NFT profiles
3 | Minting Portal | Done | 5
Sale periods definition & sales templates
Private sale for whitelisted addresses
Public sale
NTR1 claim page
5 | Redemption | Done | 7
Redemption request (phase 1)
NFC integration (phase 2)
Authentication Function (phase 3)
Admin panel function to set NFC ID
Forging
6 | Socials | Done | 3
Follow creators
Like NFTs
Collection watchlist
7 | Socials report | Pending
Report users
Report collection/NFT issues
8 | Whitelist | Done | 1
Add to whitelist
9 | Creators onboarding | Pending
Become a creator page
Process documentation
Checklist for requirements
10 | Documentation | Done
User manual documentation
11 | Corporate
Landing page
FAQ
12 | Redeployments
Redeployments NTR1
Redeployments Nayom1
13 | Admin Panel - Phygital | Done | 8
- Set redemption window
- Set redemption attributes
- NFT-NFC
- Analytics
14 | Admin Panel - Collection management | Done | 10
- Set mint limit
- Set sales period
- Slot reservation (mint hold)
- Collection profile edit
- Whitelist
- Analytics
15 | Admin Panel - User management | Done | 7
- Role & permission management
- Blacklist
16 | Security | Done
Integration with Fractal
Alert system (Launchpad down)
Tablet version*
Mobile version*
| SUM |  | 61

## 1
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 01 |  |  |  |  | 0
Module Name |  |  | User onboarding and management
Number of testcase |  |  | 14 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Web3 connection & authentication
01_1 | N | Connect as 1st user: form display | Being in platform | 1. Connect button 2. Select wallet 3. Sign the message 4. Fill textbox, agree term, submit form 5. Changes information, Save changes button | 4. Redirect to edit profile mode 5. Save changes succeed Wallet address is connected
01_2 | N | Connect as 1st user: skip form | Being in platform | 1. Connect button 2. Select wallet 3. Sign the message 4. Skip form | 4. Wallet address is connected
01_3 | N | Connect from 2nd user | Being in platform | 1. Connect button 2. Select wallet 3. Sign the message | 4. Connected
01_4 | A | Conect fail with wrong network | Being in platform | 1. Connect button 2. Select wrong network (wallet) | 2. Display error msg
01_5 | N | Connect without signing | Being in platform | 1. Connect button 2. Select wallet 3. Skip Sign the message | 3. Connected User could surf in platform, can not do the privilege actions
01_6 | N | Disconnect wallet | Connected wallet | 1. Disconnect wallet button | 1. Disconect sucessfully
01_7 | N | Switch network | Being connected the wrong network | 1. Changes network on wallet (manually) 2. Connect wallet again | 1. Switch network's success 2. Connect wallet successfully
01_8 | N | Check balances | Connected wallet | 1. Choose wallet icon on navigation bar | 1. View the balances
User profile
01_9 | N | View own user profile | Being in platform | 1. View own profile | 1. Display exactly same with UI Edit profile button's enable
01_10 | N | View other user profile | Search user in platform or Click on the avatar on platform | 1. View user profile | 1. Display exactly same with UI
01_11 | N | Edit profile (validation fields) | Being in own profile | 1. Edit profile button 2. Changes information (validation) 3. Save changes button | 2. Save changes button's active 3. The changed information is submit
01_12 | A | Edit profile (invalidation fields) | Being in own profile | 1. Edit profile button 2. Changes information (invalidation) | 2. Display error msg Save changes button's inactive
Integration with Twitter
01_13 | N | Connect Twitter | Being in edit profile mode | 1. Connect Twitter button 2. Authorised steps 3. Complete connecting twitter | 3. Display Connected
01_14 | A | Connect Twitter without finshing all steps | Being in edit profile mode | 1. Connect Twitter button 2. Not Authorised steps | 2. Not connected

## 2
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 02 |  |  |  |  | 0
Module Name |  |  | Collections
Number of testcase |  |  | 6 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Search & List collections
02_1 | N | View collections in navigation bar | Being in platform | 1. Select Collections section on navigation bar | 1. Display all upcoming/ ongoing collections in real time
02_2 | N | Search collections in search box (have results) | Clicked search box (navigation bar) | 1. Search "Nay" for searching | 1. Display the matching result
02_3 | A | Search collections in search box (not have results) | Clicked search box (navigation bar) | 1. Search "x0x1" which not have result | 1. No resutl display
02_4 | N | Click on result, open profiles | Completed this test case | 1. Click on desired result | 1. Redirect to the result page (collection page)
Collections profile
02_5 | N | View collections profile | Being in colletion page | 1. View collection page | 1. Display exactly same with UI
NFT profile
02_6 | N | View NFT profile | Being in NFT page | 1. View NFT page | 1. Display exactly same with UI

## 3
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 03 |  |  |  |  | 0
Module Name |  |  | Minting Portal
Number of testcase |  |  | 5 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Private sale for whitelisted addresses
03_1 | N | Minting flow as whitelisted user | 1. Whitelisted user 2. Presle is started 3. Sufficient | 1. Enter amount 2. Sign the mesage | 2.1. Minting processing 2.2. Minting sucessfully 2.3. Update the amount of this NFT (whole sale) Notify
03_2 | A | Minting flow as whitelisted user, insufficient balance | 1. Whitelisted user 2. Presle is started 3. Not sufficient balance | 1. Enter amount 2. Sign the mesage | 2.1. Notify insufficient balance
03_3 | A | Minting flow as not whitelisted user | 1. Not Whitelisted user 2. Presle is started | 1. View minting portal | 1. Display Get whitelisted button
Public sale
03_4 | N | Minting flow, sufficient balance | 1. Sale is started | 1. Enter amount 2. Sign the message | 2.1. Minting processing 2.2. Minting sucessfully 2.3. Update the amount of this NFT (whole sale) Notify
03_5 | A | Minting flow, insufficient balance | 1. Sale is started | 1. Enter amount 2. Sign the message | 2.1. Minting processing 2.2. Notify insufficient balance

## 4 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 04 |  |  |  |  | 0
Module Name |  |  | Claim page
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
NTR1 claim page

## 5
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 05 |  |  |  |  | 0
Module Name |  |  | Redemption
Number of testcase |  |  | 7 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Redemption request (phase 1)
05_1 | N | Redeem flow, not complete KYC | 1. User doesnt have the KYC complete 2. Being NFT owner | 1. Click KYC button 2. Go to KYC application process and finish | 2. Display pending status 3. Display the Redeem button and continue this test case
05_2 | N | Redeem flow, has completed kyc process | User has the KYC token | 1. Redeem button 2. Fill Redeem form, Submit form 3. Confirm the redemption 4. Sign the KYC and redemption message | 4. Notify complete pop-up
Authentication Function (phase 3)
05_3 | N | User is anonymous user | User scaned the product by NFC (authenticate) | 1. Open the URL from smatphone 2. Waiting for server checking the authenticy | 2. Authen: Redirect to a page which renders a product page that lists the details of the physical product and the details of its associated NFT.
05_4 | A | User is anonymous user | User scaned the product by NFC (counterfeit) | 1. Open the URL from smatphone 2. Waiting for server checking the authenticy | 2. Counterfeit: Displays the counterfeit product warning page
05_5 | N | User is logged-in desktop user | User initiated action in dektops (authentication button) | 1. Be viewed prompt of 6 digit code input 2. Scan the NFC tag product 3. Open the URL 4. Waiting for server checking the authenticy and generate 6 digit-code 5. Input the 6 digiti code | 2. Receive an URL 3. Redirect to an authentication endpoint of the platform 4. Authen: Redirect to a page which renders a product page that lists the details of the physical product and the details of its associated NFT and a 6 digit code 5. Desktop application will perform the action. (authen)
05_6 | A | User is logged-in desktop user | User initiated action in dektops (counterfeit button) | 1. Be viewed prompt of 6 digit code input 2. Scan the NFC tag product 3. Open the URL 4. Waiting for server checking the authenticy and generate 6 digit-code | 2. Receive an URL 3. Redirect to an authentication endpoint of the platform 4. Counterfeit: Displays the counterfeit product warning page, not receive a 6 digit code
Forging
05_7 | N | Redeem flow, has the kyc process complete | User has the KYC complete | 1. Redeem button 2. Fill Redeem form, Submit form 3. Confirm the payment process 4. Sign the KYC and redemption message | 4. Notify complete pop-up

## 6
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 06 |  |  |  |  | 0
Module Name |  |  | Socials
Number of testcase |  |  | 3 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Follow creators
06_1 | N | Follow creator | Being in platform | 1. Go to Creator profile 2. Follow button | 2. Change to Followed button
Like NFTs
06_2 | N | Like NFTs | Being in platform | 1. Available page for like NFTs: - NFT page - In tab which lists NFTs 2. Click Like button | 2. Change to status of Like (Liked)
Collection watchlist
06_3 | N | Add collection to watchlist | Being in collection page | 1. Button Add to watchlist | 1. Changes status of button Could see the added collection in watchlist tab (in own profile)

## 7
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 07 |  |  |  |  | 0
Module Name |  |  | Socials report
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Report users
Report collection/NFT issues

## 8
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 08 |  |  |  |  | 0
Module Name |  |  | Whitelist
Number of testcase |  |  | 1 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Add to whitelist
08_1 | N | Get whitelisted | Being in collection page (in presale) | 1. Get whitelisted button 2. Confirm Yes for pop-up 3. Waiting for approvement | 2. Redirect to Membership page

## 9
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name |  |  | Creators onboarding
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Become a creator page

## 10 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference

## 11 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference

## 12 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference

## 13
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 13 |  |  |  |  | 0
Module Name |  |  | Admin Panel - Phygital
Number of testcase |  |  | 8 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Set redemption window
13_1 | N | Set redemption window, validate start and end time | 1. Being admin roles 2. Being at Phygital section's Set redemption window (of admin panel) | 1. Select collection 2. Set start and end time (validate) 3. Set the price 4. Set the redemption window button 5. Confirm yes | 5. Notify Setting success | [5 empty] | 564
13_2 | A | Set redemption window, invalidate start and end time | 1. Being admin roles 2. Being at Phygital section's Set redemption window (of admin panel) | 1. Select collection 2. Set start and end time (invalidate) 3. Set the price 4. Set the redemption window 5. Confirm | 5. Notify "Time to must be greater than time from"
Set redemption attributes
13_3 | N | Set attributes, input | 1. Being admin roles 2. Being at Phygital section's Set attributes (of admin panel) | 1. Add attributes button 2. Fill the information, choose type: input 3. Add attribute button to add | 4. Notify "Create Attributes Successfully."
13_4 | N | Set attributes, select | 1. Being admin roles 2. Being at Phygital section's Set attributes (of admin panel) | 1. Add attributes button 2. Fill the information, choose type: select 3. Input the selection and click Add button to add the selection 4. Update attribute button to add | 4. Notify "Create Attributes Successfully."
13_5 | N | Edit attributes | 1. Being admin roles 2. Being at Phygital section's Set attributes (of admin panel) | 1. Select 1 attributes to edit and click 2. Change the information 3. Update attribute button to add | 3. Notify "Edit Attributes Successfully."
13_6 | N | Delete attributes | 1. Being admin roles 2. Being at Phygital section's Set attributes (of admin panel) | 1. Select 1 attributes to delete and click 2. Confirm yes | 2. Notify " Delete Attributes Successfully."
Admin panel function to set NFC ID
13_7 | N | Assign NFC IDs | 1. Being factory worker, admin or management roles 2. Being at Phygital section's Assign NFC IDs (of admin panel) | 1. Select collection 2. Assign button 3. Scan the NFC tag in the item by smartphone 4. Input 6 digit-code (validate code) | 3. Get a 6 digit-code 4. Processing, notify sucess
13_8 | A | Assign NFC IDs | 1. Being factory worker, admin or management roles 2. Being at Phygital section's Assign NFC IDs (of admin panel) | 1. Select collection 2. Assign button 3. Scan the NFC tag in the item by smartphone 4. Input 6 digit-code (invalidate code) | 3. Get a 6 digit-code 4. Notify wrong digit code

## 14
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 14 |  |  |  |  | 0
Module Name |  |  | Admin Panel - Collection management
Number of testcase |  |  | 10 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 1
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Set mint limit
14_1 | N | Public sale: Set mint limit | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set the mint limit (Mint limit per wallet, Mint limit per stage) 3. Finish the other information and Update button 4. Confirm Yes | 4. Notify "The redemption window for this collection has been successfully set."
14_2 | N | Private sale: Set mint limit | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set the mint limit (Mint limit per wallet, Mint limit per stage) 3. Finish the other information and Update button 4. Confirm Yes | 4. Notify "The redemption window for this collection has been successfully set."
Set sales period
14_3 | N | Public sale: Sale management, validate start and end time | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set start and end time (validate) 3. Set the other information 4. Update button to update | 4. Notify Setting success
14_4 | A | Public sale: Sale management, validate start and end time | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set start and end time (validate) 3. Set the other information 4. Update button to update | 4. Notify "Time to must be greater than time from"
14_5 | N | Private sale: Sale management, validate start and end time | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set start and end time (validate) 3. Set the other information 4. Update button to update | 4. Notify Setting success
14_6 | A | Private sale: Sale management, validate start and end time | 1. Being admin roles 2. Being at Collection management's sale management (of admin panel) | 1. Select collection 2. Set start and end time (validate) 3. Set the other information 4. Update button to update | 4. Notify "Time to must be greater than time from"
Collection profile edit
14_7 | N | Edit collection page | 1. Being admin roles 2. Being at Collection management's Edit collection (of admin panel) | 1. Select collection 2. Edit button to continue 3. Change any information 4. Save changes button to finish (in both tab) 5. Confirm Yes | 2. Open the the collection page in editting mode 5. Notify: "Update Collection Successfully"
Whitelist
14_8 | N | Slot limit, time validatation | 1. Being admin roles 2. Being at Phygital's Whitelist section (of admin panel) | 1. Select collection 2. Input the slot limit 3. Input the start, end time (validate) 4. Confirm Yes | 4. Notify " Saved successfully"
14_9 | A | Slot limit, time invalidatation | 1. Being admin roles 2. Being at Phygital's Whitelist section (of admin panel) | 1. Select collection 2. Input the slot limit 3. Input the start, end time (invalidate) 4. Confirm Yes | 4. Notify wrong of setting time |  |  |  | Fail
14_10 | N | Add user (single user) | 1. Being admin roles 2. Being at Phygital's Whitelist section (of admin panel) | 1. Select collection 2. Paste the user's address for whitelisted 3. Update button 4. Confirm Yes | 4. Notify sucess Display the added address in the below list

## 15
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 15 |  |  |  |  | 0
Module Name |  |  | Admin Panel - User management
Number of testcase |  |  | 7 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Role & permission management
15_1 | N | Assign roles, not be assigned yet account | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Paste the address account (which not be assigned yet) 2. Choose 1 role for assigning 3. Add role button | 3. Processing Notify : Add role successfully. Display the added address and assigned role in the below list
15_2 | A | Assign roles, be assigned account | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Paste the address account (which not be assigned yet) 2. Choose 1 role for assigning 3. Add role button | 3. Notify: This address already set the role
15_3 | N | Search account in the roles list well | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Type the keyword | 1. Display the matching result
15_4 | N | Remove user from list | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Remove button at the selection user 2. Confirm Yes | 2. Processing Notify: Delete successfully.
Blacklist
15_5 | N | Add user in blacklist | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Paste the address account 2. Write comment for putting in blacklist 3. Add to blacklist | 3. Notify : This address has been added to the blacklist. Display the added address in the below list
15_6 | N | Remove user in blacklist | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Remove button at the selection user 2. Confirm Yes | 2. Processing Notify: The user has been removed from blacklist.
15_7 | N | Search account in the list | 1. Being admin roles 2. Being at User management's Role and Permisstion section (of admin panel) | 1. Type the keyword | 1. Display the matching result

## 16
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 16 |  |  |  |  | 0
Module Name |  |  | Security
Number of testcase |  |  | 3 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference
Edit Feature Collection
16_1 | N | Add feature collection | 1. Being admin roles 2. Being in Feature Collection section in admin panel | 1. Add feature collection button 2. Select collection 3. Edit/ add more information for collection (for displaying) 4. Create button 5. Confirm | 5. Display on the list of feature colleciton Display on the landing page
16_2 | N | Edit (information) feature collection | 1. Being admin roles 2. Being in Feature Collection section in admin panel | 1. Edit button on the collection 2. Modify the wanted information 3. Save changes button | 1. Open collection in editting page 3. Modify sucessfully
Deploy a new collection
16_3 | N | Deploy new collection | 1. wallet with sufficient matic 2. Correctly configure env file | 1. Input variables into deploymentVariables.ts 2. Run script | Collection now exists on the launchpad

## 17 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference

## 18 (hidden)
Project name: |  |  | Dandelion x Another-1 |  | DANDELION LABS |  |  | PASS
Module ID |  |  | 6 |  |  |  |  | 0
Module Name
Number of testcase |  |  | 0 |  |  |  |  | FAIL
Created by: |  |  | Mei (Van Tran Thao) |  |  |  |  | 0
Date of creation: |  |  | 2023-01-31
Date of review:
TC ID | Type of TC | Test case title | Pre-condition | Test Steps/ Flows | Expected Result | Actual result | Query DB (if have) | Test Data (if have) | Status | Bugs reference